## Time Estimate KCE
Tasks | Summary of Work | Dependencies | Efforts (# of weeks) | Efforts (# of weeks per activity)
Core Network Architecture Design Development | Estimate of Effor to create Core Architecture |  | 1.5
Router/Switch network design | Selection of type of Switch/Router | Accurate Substation numbers and locations. |  | 0.25
Development of BOM | Based on Actual substation, actual BOM per site. |  |  | 0.25
Basic Connectivity Design | Based on location, site, distance and other equipment us of proper optics and analyze any design contraints. | Fiber distances between sites |  | 0.25
High Level Configuration Development | Based on network and design objectives use of proper protocols, protection schemes etc. |  |  | 0.25
Communications and coordination with KCE/FNC/Meeting to develop the design work | Customer/vendor meetings etc. |  |  | 0.5
GPON AccessArchitecture Design Development | Effort to create GPON Architecture |  | 4.5
GPON Access Design | Create Network Diagrams etc. | Current Design and Fiber map from KCE |  | 1
GPON Access Vendor Selection | Based on KCE fiber and customer base shor list 3 vendors, have those vendors present solutions. |  |  | 1
STB Selection | Selection of suitable STB, possibly shortlisting 2/3 candidate STB |  |  | 1
BOM/site | Create BOM per site with full details |  |  | 0.5
Meeting/Coordination with vendors/KCE/FNC | Customer/vendor meetings etc. |  |  | 1
GAP Analysis | Effort to create comparison between RFoG and GPON for Trial Customers. |  | 2
Friendly Customer GPON Design | 3 Station sites, Amalia, Sunshine, Los Cordovos |  |  | 1
Friendly Customer BOM | Create BOM for initial Trial 3 site, seemlessly migratable to full design without major impact/forklift. |  |  | 0.5
RFoG vs. GPON Gap Analysis | Compare and find delta between RFoG and GPON |  |  | 0.5
|  | Total Weeks | 8
Assumptions
Work Does not include Internet Connectivity Architecture, IP Schemes, Internet Peering, Servers, DNS, DHCP etc.