## Project Deliverables
KIT CARSON Design Solution Phase 1
Objective | Tasks | Activity | Start Date | Completion % | Target Date | Projected Date | Completed On | PRIME | Issues | Resolution | Risk | comments
Core Network Design |  |  | 2013-07-15 | 0% | 2013-08-02 |  |  | Juned Noonari
| Current Core Network Analysis | Collect Current Core Network Requirements |  | 0%
|  | Collect Current Core Network Designs/Drawings |  | 0%
|  | Collect Substation Locations/Fiber Distances etc. |  | 0%
|  | Analysis and Review of docments in hand. |  | 0%
| Core Network Design | Create Network topology Diagrams |  | 0%
|  | Create Design Documents |  | 0%
|  | Equipment Selection |  | 0%
| Core Network BOM | Create per site BOM (Trial Sites only) |  | 0%
|  | Validate BOM with Juniper |  | 0%
GPON Access Network Design |  |  | 2013-07-15 | 0% | 2013-08-16 |  |  | Juned Noonari
| Current RFoG Access Network Analysis | Collect Current Access Network Requirements |  | 0%
|  | Collect Current RFoGAccess Network Designs/Drawings |  | 0%
|  | Collect Subscriber Density fiber info, meter passing |  | 0%
|  | Analysis and Review of RFoG docments in hand. |  | 0%
| GPON Access Vendor Selection | Onsite meeting with GPON Access Vendors |  | 0%
|  | Access Vendor Solution Analysis |  | 0%
|  | Finalize Vendor Selection |  | 0%
| GPON Access Network Design Creation | Map RFoG to GPON Access Design |  | 0%
|  | Create High Level Access Topology and Design |  | 0%
|  | Create Design Documents |  | 0%
| GPON Access BOM | GPON Access Equipment Selection |  | 0%
|  | Create per site Access BOM (Trial Sites only) |  | 0%
|  | Validate BOM with Access Vendor |  | 0%