## Sheet1
KCEC RFOG vs GPON Responsibility Matrix
* FNC denotes services provided by FNC or subcontractor
Key Activities | RFOG | GPON
Plan
Head End Domain (STB, eMTA, Residential GW) | Fidelity | Fidelity
Core Transport Domain (Juniper Routing/Switching) | FNC | FNC
Access Domain (ONT, splitter/tap, substation equipment) | Pulse/CommScope | FNC
Fiber Facility Domain | Pulse | Pulse
Program Management
Program Management Ofice | Pulse | FNC
Equipment Procurement - Head End (STB, eMTA, Residential GW) | Fidelity | Fidelity
Equipment Procurement - Core Transport (Juniper Routing/Switching) | FNC | FNC
Equipment Procurement - Access (ONT, splitter/tap, substation equipment) | Pulse/CommScope | FNC
Professional Services
Fiber Engineering & Design | Pulse | Pulse
Core Transport L2/L3 Engineering & Design | FNC | FNC
Access Engineering & Design | Pulse/CommScope | FNC
HeadEnd Engineering & Design | Fidelity | Fidelity
System Integration (Access and Transport Domains) | Fidelity | FNC
System Integration (Access, Transport, and Head End Domains) | Fidelity | Fidelity
Deployment Services
Rack and Cabinet Solution (substations) | SRI | FNC
EF&I - Head End | Fidelity | Fidelity
EF&I - Core Transport | FNC | FNC
EF&I - Access equipment at substations | SRI | FNC
EF&I - Splitter/Tap and ONT | KCEC | KCEC
T&TU - Head End | Fidelity | Fidelity
T&TU - Core Transport | FNC | FNC
T&TU - Access equipment at substations | SRI | FNC
T&TU - Splitter/Tap and ONT | KCEC | KCEC
Support Service
On-site Support | KCEC | KCEC
TAC Phone Support - Head End | Fidelity | Fidelity
TAC Phone Support - Core Transport | FNC | FNC
TAC Phone Support - Access | Pulse/CommScope | FNC
NOC and OSS | KCEC/Pulse | KCEC/Pulse
Training - Head End | Fidelity | Fidelity
Training - Core Transport | FNC | FNC
Training - Access | Pulse/CommScope | FNC