## Timelines
Hrs Planned Per Activity Per Month
Tasks | Summary of Work | Dependencies | Efforts (# of weeks) | Total Activity Hrs | December | January | February | March | April | May | June
KCEC IOT Testing & Architecture |  |  |  |  | Hrs Planned Per Activity Per Month December: 2013; Hrs Planned Per Activity Per Month January: 2014
Lab Development |  |  | 2 | 80 | 32 | 48 | 0 | 0 | 0 | 0 | 0
Juniper Equipment Collection | lab equipment through Juniper or use of FNC ATSC lab (resource and hardware allocations) | Dependent on equipment delivery availablity. | 0.4 |  | Hrs Planned Per Activity Per Month December: 16
Zhone equipment Collection | Loaner equipment for KCEC through Zhone | Dependent on equipment delivery availablity. | 0.4 |  | Hrs Planned Per Activity Per Month December: 16
Physical Lab setup | Lab physical setup (ATSC lab?) | ATSC (or other) lab space, power etc resource allocation and lab setup. | 1.2 |  | Hrs Planned Per Activity Per Month January: 48
Detailed Design Development |  |  | 3 | 120 | 20 | 16 | 0 | 0 | 84 | 0 | 0
Detailed Architecture Document | Document which contains the Core and Access Architecture and its related component. | Dependent on information flow through KCEC for certain pieces, such as management, IP subneting. Note: Document will not make architecture decision for management, IP, DHCP or other IT based, it is a pssive information for the arch: document but important to finalize the doc (otherwise it will be caveats in the architecture). | 1 |  | Hrs Planned Per Activity Per Month December: 20; Hrs Planned Per Activity Per Month January: 16; Hrs Planned Per Activity Per Month April: 4
Configuration Guide Core | Guide to help configure core transport function and its failure topologies specific to the Juniper Core and its possible dependencies towards Access. Also it contains function and configurations towards ISP | Dependent on testing. | 1 |  | Hrs Planned Per Activity Per Month April: 40
Configuration Guide Access | Guide to help configure access functions and interfaces towards the Core including OLT and ONTs | Dependent on testing. | 1 |  | Hrs Planned Per Activity Per Month April: 40
Testing & Execution |  |  | 7 | 280 | 24 | 80 | 88 | 88 | 0 | 0 | 0
Functional Testing Requirements | Document which identifies and translates Network Functions and Services into features and properties to be tested based on the network elements to verify PoC and desired network architecture. This will be livind document and modified based on the test results if required. | Dependent on the architecture. | 0.2 |  | Hrs Planned Per Activity Per Month December: 8
Test Plan | Testing document developed based on the Functional Testing Requirement described above. This will be a living doument during the course of testing. | Depenent on the Funtional Testing Requirements and architecture. | 0.4 |  | Hrs Planned Per Activity Per Month December: 16
Test Execution | Actual Testing and results stored in Test plan. | Dependent physical lab setup. | 6.4 |  | Hrs Planned Per Activity Per Month January: 80; Hrs Planned Per Activity Per Month February: 88; Hrs Planned Per Activity Per Month March: 88

## Reference
cost / hr | 87.5
cost / week | 3281.25
Total hrs/week | 40
loaded rate 2011 | 85.4